## Survey
Project 360
Your Name | JD Francis, Drew Fulsom, David Kim, Justin Suh
Team Name | DJ2 Studios
Project | GEM
1) Please re-iterate the SDLC methodology you have used on your project. Were there any variations made to the process over and above the text book definition of the process. If agile was used, state the number of sprints executed. How many test phases were executed i.e. besides unit testing , was integration and system testing performed? | To be filled collectively by all team members
We used an Agile SCRUM methodology. There were a total of 2 sprints.
2) Summarize the overall experience of the project and write your personal reflections on this project (what has gone well? What problems did you encounter?) | To be filled collectively by all team members
We learned the value (rather the importance) of properly planning out sprints.

## Effort
Man Hours spent on each phase
Team Members | Feasibility Study | Requirement | Design | Development | Test | Man Hours
JD | 3 | 6 | 5 | 15 | 2 | 31
David | 3 | 6 | 5 | 15 | 2 | 31
Justin | 3 | 5 | 3 | 8 | 8 | 27
Drew | 3 | 6 | 3 | 7 | 8 | 27
Total | 12 | 23 | 16 | 45 | 20 | 116
Effort % | 0.10345 | 0.19828 | 0.13793 | 0.38793 | 0.17241

## Testcases
|  | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Layers | Testcases executed | Testcases Passed | Testcases Passed | Testcases Passed | Testcases Passed
Front End | 25 | 2 | 12 | 18 | 23
Back End | 34 | 7 | 16 | 23 | 33
Total | 59 | 9 | 28 | 41 | 56
Pass Rate |  | 15.25% | 47.46% | 69% | 95%

## Defects found
|  | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Layers | Team Member | Defects found | Defects found | Defects found | Defects found
These are just suggestions. Please edit or add more based on your project decomposition | Which Team member(s) were assigned to layers | It is possible a failed TC could have more than 1 defect. Please document accordingly.
Front End | JD, David | 152 | 89 | 43 | 8
Back End | Drew, Justin | 16 | 34 | 29 | 2
Total |  | 168 | 123 | 72 | 10
Defect/LOC |  | 0.178 | 0.066 | 0.02 | 0.003

## LOC
Layers | Team Member | LOC
These are just suggestions. Please edit or add more based on your project decomposition | Which Team member(s) were assigned to layers
Front End | JD, David | 1843
Back End | Drew, Justin | 1369
Total LOC |  | 3212
Total Productivity (LOC/Effort) | Effort is counted over all units of work incl. feasibility, requirement etc. | 27.6897